# Lighthouse Sprint Master Operations Guide

The overarching playbook for sprint execution, roles, communication, and quality gates.

## 1. Sprint Lifecycle Overview

The Lighthouse Sprint methodology spans four continuous phases. Each phase builds on the previous, with formal gates ensuring quality and stakeholder alignment.

| Phase | Duration | Key Deliverable | Gate |
| --- | --- | --- | --- |
| Discovery | 2 weeks | Discovery Report | Gate 1: Go/No-Go |
| Redesign | 2 weeks | Redesign Blueprint | Gate 2: Client Sign-Off |
| Build | 3–7 weeks | Deployed Agents | Gate 3: Metrics Pass |
| Handoff | 1 week | Operator-Ready System | Gate 4: Independence |

## 2. Role Responsibilities

### Umbra Studio Roles

- Sprint Lead – Owns overall sprint delivery, daily standups, gate facilitation, risk escalation.

- Agent Engineer – Designs and builds agents, maintains spec sheets, leads deployment cycle.

- Governance Architect – Designs monitoring, alerting, escalation; owns governance wrapper implementation.

### Client Roles

- Project Sponsor – Budget, strategic alignment, escalation authority.

- Workflow Subject Matter Expert – Provides process knowledge, validates design decisions.

- Operations Lead/Future Operator – Will run the system post-handoff; participates in training and supervised operation.

## 3. Communication Cadence

| Cadence | Participants | Purpose |
| --- | --- | --- |
| Daily Standup | Studio team + SME | Status, blockers, next steps |
| Weekly Demo | Full team + sponsor | Show progress, gather feedback |
| Gate Review | Full team + sponsor | Formal decision point, go/no-go |

## 4. Template Usage Map

Each template in the Lighthouse Kit is deployed at a specific phase and serves a distinct purpose.

| Template | Phase | Primary User | Output |
| --- | --- | --- | --- |
| Workflow Audit | Discovery | Observers | Bottleneck matrix |
| Baseline Metrics | Discovery | Data analyst | Success thresholds |
| Redesign Blueprint | Redesign | Engineer | Agent specs & gates |
| Agent Spec Sheet | Build | Engineer | Build & test plan |
| Operations Manual | Handoff | Operator | Day-to-day runbook |
| Governance Runbook | Build + Handoff | Operator | Incident response |

## 5. Quality Gates Checklist

### Gate 1: Discovery Complete (End of Week 2)

- Workflow audit completed: all process steps observed and bottlenecks scored

- Baseline metrics collected and validated

- Stakeholder interviews synthesized; key themes documented

- Discovery Report signed off by sponsor; decision: proceed or iterate

### Gate 2: Redesign Approved (End of Week 4)

- Redesign Blueprint complete: all processes mapped to agents or manual steps

- Agent specifications drafted (not yet built)

- Governance gates identified and placement approved

- Client sign-off on full design (SME + Sponsor)

### Gate 3: Build Complete (Variable Timing)

- All agents deployed and running in parallel with manual workflow

- Monitoring and alerting live; governance wrapper operational

- Baseline metrics exceeded by 20% or success criteria met

- Integration testing complete; no SEV-1 incidents in last 5 days

### Gate 4: Ready for Handoff (Final Week)

- Operator training complete; operator demonstrates competency

- Supervised operation period (1 week) complete with zero critical incidents

- All documentation delivered and reviewed (manuals, specs, runbook)

- Outcome deltas measured and reported; patterns extracted and cataloged

## 6. Risk Escalation Protocol

Issues are categorized by severity and escalated based on impact and timeline.

| Level | Definition | Escalate To | Response SLA |
| --- | --- | --- | --- |
| SEV-1 | Blocks gate or sprint completion | Sprint Lead + Sponsor | 1 hour |
| SEV-2 | Blocks task or agent completion | Sprint Lead | 4 hours |
| SEV-3 | Impacts timeline but not critical | Team + SME | 1 day |
| SEV-4 | Documentation or process issue | Sprint Lead | 1 week |

## 7. Timeline Variants

### Discovery-Only (2 weeks)

- For organizations gathering intelligence before committing to build.

- Deliverable: Discovery Report + Baseline Metrics; ends at Gate 1 decision.

### Standard Sprint (6–10 weeks)

- Discovery (2 weeks) + Redesign (2 weeks) + Build (3–6 weeks) + Handoff (1 week).

- Covers most customer workflows with 2–4 agents. Operator ready within timeline.

### Extended Sprint (10–16 weeks)

- For complex workflows requiring 5+ agents, extensive integration, or governance redesign.

- Build phase extends to 6–10 weeks with parallel feature development and testing.

- Handoff extends to 2 weeks with extended supervised operation.

### LATAM Variant

- Standard timeline adjusted for 2–3 hour timezone delays.

- Standups held at split times (one Studio-focused, one Client-focused); async documentation.